## Q&A Management Sheet
Q&A Management Sheet
Project Code:
Q&A Manager:
| Last updated date | 2017-08-03 12:07
| No of Open items | 0
| No of In progress items | 0
| No of Closed items | 14
| No of Cancelled items | 0
| Total | 14
No | Location | Question | Answer | Priority | Created On | Created By | Assigned To | Deadline | Answered On | Status | Conclusion | Question Type | Title | Process | Notes | Reference
1 | Hotel's information | 1) Hotel's name 2) Address 3) Room quantity 4) Room types | 1) Ánh Dương Hotel 2) Tuan Chau Island - Halong - Quang Ninh province 3) 40 rooms 4) Single bed room, Double bed room, Twin bed room, Extra bed room | Medium | 2017-05-10 | QuyenTB | Customer | 2017-05-17 | 2017-05-12 | Closed |  | Clarification |  | Requirement
2 | Room type detail | 1)Maximum number of adult and children for each room type. 2)Number of bed of each room type | 1) - single bed room: adult: 1 children: 1 - double bed room: adult: 2 children: 1 - extra bed room: adult: 3 children: 3 - twin bed room: adult: 2 children: 2 2) - single bed room: 1 single bed - double bed room: 1 double bed - extra bed room: 3 single beds or 1 double bed and 1 single bed - twin bed room: 2 single beds | Medium | 2017-05-10 | QuyenTB | Customer | 2017-05-17 |  | Closed
3 | Hotel's structure | 1) How many department? 2) Each department's activities? 3) How many staff in each department? (or total staff) | 1) There are 7 departments: Director, Manager, Room department, Receptionist, Restaurant, Kitchen, Security 2) + Director: Owner of the hotel, receives reports and solves the problems which was given by the manager. + Manager: supervise, manage staffs, finance, hotel's increment strategy. Have a responsibility to report all the relating problems to the director. + Room department: clean rooms, guaarant the accessory in each room. + Receptionist: take the responsibility of a receptionist. + Kitchen: take responsibility in cooking area including cook, clean, etc ... + Restaurant: receive guest's requests and serve. + Security: maintain the security of the hotel and help guests carrying their luggages. 3) Total staffs: about 25 people | Medium | 2017-05-10 | QuyenTB | HungNV | 2017-05-17 |  | Closed
4 | Hotel's activities | 1) Does the hotel receive to hold events? 2) Yearly event. | 1) + 2) Because of the hotel have just been builded so haven't have those services. | Medium | 2017-05-10 | QuyenTB | HungNV | 2017-05-17 |  | Closed
5 | Hotel's infrastructure | 1) Accessories in each room are the same or different? 2)What are the differences? | 1) Accessories in each room are the same. 2) N/A 3) Room department will manage and provide accessories. | Medium | 2017-05-10 | QuyenTB | HungNV | 2017-05-17 |  | Closed
6 | Accessories management | 1) Who manage accessories? 2) Manage following room or room type? | 1) Accessories are managed by room department. 2) Accessories are managed following room type. | [6 empty] | Closed
7 | Accessories detail | What including in each room (or room type)? | refer accessory_detail.xls document. | [6 empty] | Closed
8 | Guest book room offline | 1) Method of implementation? 2) Required parts to be able to search? 3) How many rooms and people can book for in each time? Why? 4) How to book room for individual? 5) Book rooms for group: from tourist company, tourist guider, etc? 6) What are included in or not included in payment method? 7) Individual payment method? 8) Payment method for group? | 1) Guest book for room by calling or book directly at reception. Receptionist will search for room following guest's request, check-in, check-out and confirm payment for guest. 2) Require check-in and check-out date, number of people and rooms to search (required). 3) Unlimited. 4) a person, family. 5) Tourist companies, tourist guiders will represent to book. 6) Payment methods: +) cash and card +) Prepay and postpay +) Incentive: none +) The amount include room's price and attached services - for example: laundry, etc ..., not including other incurred costs. 7) No incentive. 8) Represented person pay for group or each person pay for themselve. | High | 2017-05-10 | QuyenTB | HungNV | 2017-05-17 |  | Closed
9 | Guest book room online | 1) Method of implementation? 2) Required parts to be able to search? 3) How many rooms and people can book for in each time? Why? 4) How to book room for individual? 5) Book rooms for group: from tourist company, tourist guider, etc? | 1) Perform on hotel's website. List of available rooms will be shown depend on search conditions. 2) Search conditions: check-in and check-out date, number of adult, children and rooms. 3) Each time, the maximum of booking is 4 rooms, each room 2 adult and 2 children (depend on room type) 4) A person book on website. 5) Tourist companies, tourist guiders will represent to book. | High | 2017-05-10 | QuyenTB | HungNV | 2017-05-17 |  | Closed
10 | Online payment | 1) What are payment method? 2) What parts are included in the total amount? 3) Payment individually or by group have incentive? 4) Guest's information. 5) Confirmation way. | 1) Pay through e-banking, visa, master by 100% the total amount. 2) The amount include room's price and attached services - for example: laundry, etc ..., not including other incurred costs. 3) No incentive. 4) Full name, phone number, email, identity number. 5) Confirm booking by 2 ways: - By email: system will send successfully booking information to guest's email. - Phone number: receptionist will call to notify booking status for guest. | High | 2017-05-10 | QuyenTB | HoangVT | 2017-05-17 |  | Closed
11 | Change booking (online booking) | 1) Changeable time? 2) Changeable things? 3) Does it cost extra? 4) Changing method? 5) Is it able to cancel booking? | 1) Anytime before check-in time. 2) - change number of room, people but not exceed limited quantity. - change attached services: meals, laundry, etc. - change booked room type. - change check-in and check-out time. 3) Extra cost will depend on room type and attached services. - Change to same room type, same services --> cost unchanged. - Change to better room type: extra cost = better room type's price - booked room type. - Service: extra cost will depend on each service: +) New service's price - booked service's price > 0 --> must pay +) New service's price - booked service's price <= 0 --> no need to pay - Change room when check-in: +) Cause from hotel: change to the same room type or better room type with out extra cost. In case that there are no available room, change to worse room type if guest accepted and hotel must return difference cost to guest. +) Guest want to change: a) Change to better room type must pay extra cost. b) Change to the same room type without extra cost. c) Change to worse room type without returning difference cost. - Change room after check-in: +) Cause from hotel: a) Change to the same room type and cost unchanged. b) Change to better room type and cost unchanged c) Change to worse room type if guest accepted and hotel must return difference cost to guest. +) Cause from guest: Extra cost will depend on room type, difference cost between booked room's left cost and new cost in the same time. - Change check-in and check-out time: Redo searching for room with new check-in and check-out time, guest must pay for difference cost. 4) Call to hotel's reception or make change on website, depend on booked code to change or cancel booking. 5) Guest want to cancel booking: - In the first 24 hours since booked for room: guest must pay for 10% of amount. - From 24 hours to 72 hours: guest must pay for 50% of the amount. - After 72 hours and before 0 o'clock of check-in day: guest must pay 50% of the amount. - Cancel on check-in day: won't be returned. | High | 2017-05-10 | DucDD | QuyenTB | 2017-05-17 |  | Closed
12 | Manage guest's information | 1) What information will be managed? | 1) - Full name, identity number, address, phone number. - Booked room's information including: room number, room type, check-in and check-out time, attached services. | Medium | 2017-05-10 | DucDD | QuyenTB | 2017-05-17 |  | Closed
13 | Manage check-in guest | 1) Guest book individually or by group. 2) Confirm guest's booked room is correct. 3) Check-in method. 4) Are there any extra services? | 1) - Check-in by group: +) Get representation's information including: phone number, fullname, identity number (and other guests in group if able) +) Number of people, adult, children, oldster, disabled people, etc. +) Check-in time - Check-in individually: +) Get personal information one by one. +) Check-in time. 2) Confirm guest's information and booked room by booked code or identity number. 3) Show one of below information at reception: identity card, phone number, booked code and check-in following receptionist's guideline. 4) Depend on guest's demand, if there are any extra code, it will be notified to guest and guest will have a bill for it | High | 2017-05-10 | DucDD | QuyenTB | 2017-05-17 |  | Closed
14 | Manage check-out guest | 1) Check-out by group: - Check-out method. - Payment method. 2) Check-out individually: - Check-out method. - Payment method. 3) Did guest satisfy with room and hotel's services? (Get review) | 1) Check-out by group: - Return room: +) Guest return room to hotel before 12 o'clock of check-out day in reservation. +) Receptionist will cancel booking for guest on system. +) Staff will check room and accessories carefully before check-out for guest. - Payment: +) With guest who paid 100% before check-in: print bill including room, extra services, penalty (if there are lost and broken accessories or damaged to room). +) With guest who book offline: pay cash or by visa card, master card, JVC. +) Returning room before check-out day will not receive change. +) Late check-out case, depend on guest's demand, there will be late check-out by day or by time. 2) Check-out individually - Return room: +) Before 12 o'clock of check-out day. +) Even if check-out sooner, it'll still be regarded as 12 o'clock of check-out day. +) Staff will check for room, accessories before guest check-out and confirm penalty (if there are lost and broken accessories or damaged to room). +) Receptionist will do check-out for guests of that room one by one. - Payment: +) With guest who paid 100% before check-in: print bill including room, extra services, penalty (if there are lost and broken accessories or damaged to room). +) With guest who book offline: pay cash or by visa card, master card, JVC. 3) Rating by a survey which will be given to guests. | High | 2017-05-10 | DucDD | QuyenTB | 2017-05-17 |  | Closed