## Sheet1
MEETING MINUTES
Project Code: |  | HOWE |  | Conductor: | Phan Truong Lam |  | Date: | 2017-07-11 09:00
Project Manager: |  | Nguyen Viet Hung |  | Secretary: | Vu Tran Hoang |  | Venue: | FPT Hoalac Campus 105R
List of Attendees
No | Full Name |  |  |  | Unit/Group | Position |  | Attendance
1 | Phan Truong Lam |  |  |  |  | Instructor |  | Present
2 | Nguyen Viet Hung |  |  |  |  | Leader |  | Present
3 | Vu Tran Hoang |  |  |  |  | Member |  | Present
4 | Dang Cong Son |  |  |  |  | Member |  | Present
5 | Dang Duc Manh |  |  |  |  | Member |  | Present
6 | Tran Ba Quyen |  |  |  |  | Member |  | Present
TOPIC OF MEETING
AGENDA
- Review Sequence Diagram - Review Room Type Manager Function & Login Function
CONTENT
- Review and edit Sequence Diagram - Review and edit UI of Room Type Manger - Review coding convention - Review function search, create new and update of Room Type Manager
CONCLUSION
No | Discussed Items |  | Decisions |  |  |  |  | PIC | Deadline
1 | Review and edit Sequence Diagram |  | Complete sample of Login Function |  |  |  |  | QuyenTB, SonDC | 2017-07-17
2 | Review and edit UI of Room Type Manager |  | Complete Room Type Manager Function |  |  |  |  | ManhDD | 2017-07-17
3 | Review coding convention |  | Complete Coding Convention |  |  |  |  | SonDC | 2017-07-17
4 | Review function search, create new and update of Room Type Manager |  | Complete function of RoomType Manager |  |  |  |  | SonDC | 2017-07-17
Note on L35: Fill the name of PIC (Person-in-charge) if needed. Otherwise, leave the cell 'BLANK'
Note on M35: Fill the date if needed. Otherwise, leave the cell 'BLANK'