## Sheet1
MEETING MINUTES
Project Code: |  | HOWE |  | Conductor: | Phan Truong Lam |  | Date: | 2017-07-25 09:00
Project Manager: |  | Nguyen Viet Hung |  | Secretary: | Vu Tran Hoang |  | Venue: | FPT Hoalac Campus 105R
List of Attendees
No | Full Name |  |  |  | Unit/Group | Position |  | Attendance
1 | Phan Truong Lam |  |  |  |  | Instructor |  | Present
2 | Nguyen Viet Hung |  |  |  |  | Leader |  | Present
3 | Vu Tran Hoang |  |  |  |  | Member |  | Present
4 | Dang Cong Son |  |  |  |  | Member |  | Present
5 | Dang Duc Manh |  |  |  |  | Member |  | Present
6 | Tran Ba Quyen |  |  |  |  | Member |  | Present
TOPIC OF MEETING
AGENDA
- Review UI of Booking Offline Function - Review Booking Offline - Review Sequence diagram of Booking Offline Function - Review Test Plan
CONTENT
- Review and edit UI of Booking Offline Function - Review and edit Booking Offline - Review and edit Sequence diagram of Booking Offline Function - Review and edit Test Plan
CONCLUSION
No | Discussed Items |  | Decisions |  |  |  |  | PIC | Deadline
1 | Review and edit UI of Booking Offline Function |  | Complete UI of Booking Offline Function |  |  |  |  | ManhDD | 2017-07-31
2 | Review and edit Booking Offline |  | Complete function Booking Offline |  |  |  |  | HungNV | 2017-07-31
3 | Review and edit Sequence diagram of Booking Offline Function |  | Complete Sequence diagram of Booking Offline |  |  |  |  | QuyenTB | 2017-07-31
4 | Review and edit Test Plan |  | Complete Test Plan |  |  |  |  | QuyenTB, HoangVT | 2017-07-31
Note on L35: Fill the name of PIC (Person-in-charge) if needed. Otherwise, leave the cell 'BLANK'
Note on M35: Fill the date if needed. Otherwise, leave the cell 'BLANK'