## MeetingMinutes
MEETING MINUTES
Project Code: |  | HOWE |  | Conductor: | Phan Truong Lam |  | Date: | 2017-05-09 09:00
Project Manager: |  | Nguyen Viet Hung |  | Secretary: | Vu Tran Hoang |  | Venue: | FPT Hoalac Campus 105R
List of Attendees
No | Full Name |  |  |  | Unit/Group | Position |  | Attendance
1 | Phan Truong Lam |  |  |  |  | Instructor |  | Present
2 | Nguyen Viet Hung |  |  |  |  | Leader |  | Present
3 | Vu Tran Hoang |  |  |  |  | Member |  | Present
4 | Dang Cong Son |  |  |  |  | Member |  | Present
5 | Dang Duc Manh |  |  |  |  | Member |  | Present
6 | Tran Ba Quyen |  |  |  |  | Member |  | Present
TOPIC OF MEETING
AGENDA
- Review actions that team has deployed - Create list of tasks that must be done before the next meeting
CONTENT
- Hotel's operation - Describe details of the system - Process development
CONCLUSION
No | Discussed Items |  | Decisions |  |  |  |  | PIC | Deadline
1 | Hotel's operation |  | Analyze all of the hotel's operation |  |  |  |  | Team Member | 2017-05-11
2 | Describe details of the system |  | Describe details of the system by paragraph |  |  |  |  | HungNV | 2017-05-16
3 | Analyze process development |  | Study about SRS, Use Case Diagram, Process of Development |  |  |  |  | Team Member
Note on L35: Fill the name of PIC (Person-in-charge) if needed. Otherwise, leave the cell 'BLANK'
Note on M35: Fill the date if needed. Otherwise, leave the cell 'BLANK'